## Sheet1
Slno | Installation observations | Office test Observations
1 | No details regarding charger indication Stable Green, Green/Red blinking, Stable Red | After the battery is fully drained, when the charger is connected, the charger LED blinks green and red for approximately 10 seconds (the exact duration needs to be verified again). After that, while the battery is charging, the charger LED remains solid red.
2 | After fully drained the system takes more than 1 hr for turning on | During office testing, the system powered on within a minutes. The Mini PC does not power on automatically. After pressing the power button on the back side, the Mini PC powers on within 27 seconds.
3 | No details regarding Battery LED for low battery, backup time after low battery, charge in progress(yellow/green blinking, not distinguishable ), full charge condition Red | 1.The low battery indication is not displayed. 2.During charging, the battery LED blinks pale yellow and green, but the colors are not clearly distinguishable. 3.After removing the charger, the battery LED changes to solid green.
4 | Automatically not turned on, We need to press on back side of the panel | Yes need to press power button
5 | Cable got broken after starting the demo
6 | If battery is fully drained the date and time not coming correctly. | Here it is updated with correct date and time( refer teams photo I shared in bsh group).
7 | Custom image in Splash screen (BIOS),
8 | Wifi showed very low signal strength and got disconnected automatically | The Wi-Fi connected successfully to both the office Wi-Fi network and the mobile hotspot. when attempting to join a Microsoft Teams call, the device restarted automatically.
9 | BSH requested minimum 2 hrs battery backup
10 | The sensors make and models spare required
11 | The system shows noticeable heat test with carrycase, identify the component | Need to test
12 | Windows OS automatically restarting Due to improper shutdown | This automatic restart was observed while using Wi-Fi during a Microsoft Teams call.
13 | 1. Windows optimization (disable swap/virtual memory 2. Windows embedded => Contact Thinvent (Venumadhav) 1. Windows 11 IoT Enterprise: The latest iteration providing the full power, security, and compatibility of Windows 11 for high-end specialized devices. 2. Windows 10 IoT Enterprise: A widely used, enterprise-grade version offering long-term servicing channels (LTSC)
14 | BSH require sensors with 5m Cable
15 | Display is hanging Due to OS issue | HANGING NOT OBSERVED.RESTART OBSERVED.
16 | Touch screen lag due to low battery/ charging after deep discharge noticed in lab testing 1. Repeat test | OBSERVED Again
17 | BSH wants spare for critical items
18 | If this portable unit doesn’t work, BSH will use device , power adaptor and software Use host name in device | The Mini PC is switched off. The device is connected to the laptop using the front-panel LAN port, and the application is connected. Data acquisition is happening successfully.
19 | Date and time changed when power switched ON Fully drained battery Due to multiple power off | Not observed here time and date updated correctly
20 | OS crashed unit is not turned on after pressing the back side button, 2 times the main screen coming after that is closed, again ON automatically. after opening mainscreen and connected our AS then within 1 minute the display has turned off but battery led and error led, power led ON condition(may be power is not sufficient) minipc is taking 15-20 sec initially after pressing back side of the button
21 | BSH require one more usb port for keyboard
22 | Exhaust fan required Decide after Thermal test for 3 hours | Need to test
23 | WiFi connection with mobile hotspot | connected both network sucessfully
24 | The charging time is stated to be 2 hours;however, from our operational perspective, a shorter charging duration would be preferred.
25 | In the event of a failure of any critical component, please provide the troubleshooting procedure and the expected time for repair or replacement. ,